## Project Schedule
OJ & the Cowboy Hats Work Schedule |  |  | http://bit.ly/34ZvXyr
PROJECT NAME
Work Schedule
KEY
I = Individual Work
TIMELINE
PHASE TITLE | START DATE | END DATE | DURATION in days | DURATION in hours | DURATION in hours per member (Avg) | COMMENTS
Iteration 1 | [5 empty] | Due Date: 2/1/24
Personas - I | 2024-01-26 | 2024-02-01 | 6 | 144 | 20.5714
Workflow - Information Architecture | 2024-01-19 | 2024-02-24 | 36 | 864
Key I/O and Other I/O - I | 2024-01-26 | 2024-03-25 | 59 | 1416 | 202.2857
Test User Interface for Module - I | 2024-01-26 | 2024-03-25 | 59 | 1416 | 202.2857
Work Package 1 | [5 empty] | Due Date: 2/08/24
Software Requirements Specification (SRS)- I | 2024-01-12 | 2024-04-16 | 95 | 2280 | 325.7143
Project Schedule | 2024-01-24 | 2024-02-01 | 8 | 192
Coding Standards | 2024-01-12 | 2024-02-01 | 20 | 480
Defect Tracking Policy | 2024-01-26 | 2024-02-01 | 6 | 144
Personas | 2024-01-26 | 2024-02-01 | 6 | 144
System Architecture - I | 2024-01-26 | 2024-02-01 | 6 | 144 | 20.5714
UX Architecture (Garret Diagrams) - I | 2024-01-26 | 2024-02-01 | 6 | 144 | 20.5714
User Interface Desgin - I | 2024-01-26 | 2024-03-25 | 59 | 1416 | 202.2857
Risk Assessment - I | 2024-01-29 | 2024-02-01 | 3 | 72 | 10.2857
Iteration 2 | [5 empty] | Due Date: 2/22/24
Sub-System User Interface - I | 2024-02-06 | 2024-03-03 | 26 | 624 | 89.1429
Key I/O and Other I/O Work - I | 2024-02-10 | 2024-02-22 | 12 | 288 | 41.1429
Test UI for I/O - I | 2024-02-01 | 2024-02-22 | 21 | 504 | 72
Work Package 2 | [5 empty] | Due Date: 3/07/24
Scrum Boards | 2024-02-01 | 2024-03-07 | 35 | 840
User Stories | 2024-02-14 | 2024-03-07 | 22 | 528
Architecture & Design | 2024-02-11 | 2024-03-07 | 25 | 600
Test Plans - I | 2024-02-03 | 2024-02-25 | 22 | 528 | 75.4286
System Architecture & Design (SDD) - I | 2024-02-16 | 2024-03-07 | 20 | 480 | 68.5714
Design Review | [5 empty] | Due Date: 3/07/24
Software Architecture - I | 2024-02-05 | 2024-02-22 | 17 | 408 | 58.2857
Use Case Diagram - I | 2024-02-12 | 2024-02-22 | 10 | 240 | 34.2857
Class Diagram - I | 2024-02-12 | 2024-02-22 | 10 | 240 | 34.2857
Sequence Diagram - I | 2024-02-12 | 2024-02-22 | 10 | 240 | 34.2857
Deplyment DIagram - I | 2024-02-12 | 2024-02-22 | 10 | 240 | 34.2857
Iteration 3 |  |  | 0 |  |  | Due Date: 4/04/24
Sub-System User Interface - I | 2024-01-26 | 2024-03-25 | 59 | 1416 | 202.2857
Intergration | 2024-03-02 | 2024-04-24 | 53 | 1272
User Interface Input/Output Tests | 2024-02-29 | 2024-03-27 | 27 | 648
Train move from Yard to Destination Block | 2024-02-24 | 2024-04-01 | 37 | 888
Work Package 3 | [5 empty] | Due Date: 4/25/24
Presentation - Iteration 4 | 2024-04-12 | 2024-04-25 | 13 | 312 |  | Due Date: 4/25/24
Work Schedule | 2024-04-15 | 2024-04-22 | 7 | 168
Configure Management | 2024-04-17 | 2024-04-23 | 6 | 144
Bug Reports | 2024-04-18 | 2024-04-22 | 4 | 96
Video of System Functionality | 2024-04-23 | 2024-04-23 | 0 | 0
Code Base - I | 2024-01-16 | 2024-04-24 | 99 | 2376 | 339.4286
Instalation Manual - I | 2024-04-19 | 2024-04-21 | 2 | 48 | 6.8571
Test Plan - I | 2024-04-20 | 2024-04-22 | 2 | 48 | 6.8571
Final Subsystem Simulation | 2024-04-20 | 2024-04-25 | 5 | 120
Formulas:
DURATION in days = DATEDIF([START DATE], [END DATE], "D")