## Sheet1
Risk | Risk Probabilty | Risk Severity | Mitigation
Final product is not done on time. | Moderate | Fatal | We stick to our consistent schedule and fully integrate.
Someone is sick and connot finish. | Low | Fatal | We give ourselves enough time for disater situations to recover.
Integration is a failure. | Moderate | High | We focus on integrating continously through the semester.
Nonworking branch is set to Main in Git. | High | Moderate | We carefully review all pull requests and have appropriate users checking off.
A requirement is not implemented/finished | Moderate | Moderate | We carefully review all requirements and clearly divide work appropriately.
Hardware implementation fails | Low | Moderate | Have a second microcontroller.
Github commit/push doesn't go through | Moderate | High | We will keep local backups.
Software executable fails on presentation computer. | Low | High | We will ensure that the executable runs on Windows 10.
A member has to miss a meeting. | High | Low | Meeting notes will be taken.